## Sheet1
Risk Description | Initial Risk Score (1 - unlikely / 10 likely) | Preventitive Measures | Score after preventitve Measures
Not finishing on time | 8 | -Stick to the miles stones set out in the project spec -Now more comfortable with Java so should go better than last time | 5
Database getting hacked | 8 | -Do not send passowrds and usernames to Github -Do not leave instances running when not needed -Set difficult passwords to hack | 2
Running out of credit on GCP | 5 | -Turn instances off when not needed -Set reminders on laptop to remind me at the end of the day | 2
Application not working | 7 | -Now more familiar with techologies -Seek help sooner rather than later -When something isn't working - write down questions of what I don't understand so that I don't make the same mistake again | 6
First draft of wireframe - too ambitious | 6 | Review the design as I go along and make changes to parts that are difficult to pull off | 3
SQL tables not formatted correctly | 5 | -Should be better than last time as I have a better understanding -I must fix the tables as soon as I spot a mistake -Seek clarification if needed | 3
Getting lost in project and loose sight of what is important | 8 | -Keep Jira board up to date -Set entities that are part of the MVP as top priority and takle those issues first | 2
Spending too much tim on the look of the applcation before focusing on if it is working | 7 | -Leave CSS until the applciation is working | 4